## Jira User Stories Backlog
Project Backlog & Acceptance Criteria (Jira)
Issue Key | Epic | Summary | User Story | Acceptance Criteria (Gherkin) | Priority | Story Points
OMNI-101 | Data Ingestion | Snowflake to SFMC Automated Audience Import | As a Campaign Specialist, I want automated nightly imports from Snowflake to SFMC Data Extensions, so that my audiences are always fresh without manual CSV uploads. | Given a new delta file is dropped in SFTP by 02:00 AM, When Automation Studio runs the import activity, Then data is populated into 'DE_Member_Master' with 0 duplicate SubscriberKeys. | High | 5
OMNI-102 | Journey Builder | Fall-back Trigger to SMS on Email Inaction | As a Marketing Manager, I want Journey Builder to trigger an SMS if an email is unread after 48 hours, so that we maximize appointment compliance. | Given a member is sent an Email, When 'Email Open' event is false after 48 hours AND SMS_OptIn is True, Then route member to MobileConnect SMS activity. | High | 8
OMNI-103 | Telephony | AcuCall IVR Auto-Dial Trigger for Unconfirmed Bookings | As a Care Coordinator, I want critical care reminders escalated to automated IVR calls, so that high-risk members do not miss preventive screenings. | Given a member has an open care gap > 15 days, When reached in journey step 4, Then make an outbound API payload call to AcuCall IVR with Member_ID and Callback_Slot. | Medium | 5
OMNI-104 | Compliance | TCPA Quiet Hours and Consent Suppression | As a Compliance Officer, I want dynamic blocking of voice/SMS outside local legal hours, so that the organization avoids TCPA violations. | Given a member's local time zone is EST, When a trigger occurs before 08:00 AM or after 21:00 EST, Then suppress the dispatch until 09:00 AM local time. | Critical | 3
OMNI-105 | Contact Center | NICE CXone Queue Integration for Campaign Callbacks | As a Contact Center Agent, I want warm campaign leads routed directly to my CXone desktop, so that I can assist members who request live callbacks. | Given a member texts 'AGENT' in response to an SMS, When the webhook hits NICE CXone API, Then create an inbound skill-based task for available agents within 30 seconds. | High | 5

## Data Mapping & Integration
Source-to-Target Data Mapping Specification
Source System | Source Table | Source Field | Target System | Target Data Extension | Target Field | Data Type | Transformation / Business Logic
Snowflake | MEM_MASTER | MEMBER_ID | SFMC | DE_Member_Master | SubscriberKey | Text (50) | Primary Key; MD5 hashed identifier
Snowflake | MEM_MASTER | FIRST_NAME | SFMC | DE_Member_Master | FirstName | Text (100) | InitCap formatting
Snowflake | MEM_MASTER | CELL_PHONE | SFMC | DE_Member_Master | Phone_Number | Phone | E.164 standard formatting (+1XXXXXXXXXX)
Snowflake | MEM_CONSENT | SMS_OPT_IN_FLAG | SFMC | DE_Member_Master | SMS_OptIn | Boolean | Convert 'Y/N' to 'True/False'
Snowflake | MEM_CONSENT | LAST_OPTIN_DATE | SFMC | DE_Member_Master | Consent_Timestamp | Date | Must be <= Current Date
Snowflake | MEM_CLINICAL | CARE_GAP_CODE | SFMC | DE_Campaign_Audience | Care_Gap_Type | Text (50) | Map code to descriptive campaign bucket
SFMC | DE_Campaign_Tracking | Call_Outcome | NICE CXone | CALL_DISPOSITION_QUEUE | Disposition_Status | Text (30) | Sync via REST API for abandoned IVR follow-ups

## UAT & RTM Matrix
Requirements Traceability Matrix & UAT Execution
Requirement ID | Jira Key | Test Scenario | Expected Outcome | Status | Sign-Off Role
FR-01.1 | OMNI-101 | Validate delta record import from Snowflake SFTP | 50,000 records loaded; invalid records logged | Passed | Data Architect
FR-02.1 | OMNI-102 | Test Email-to-SMS fallback sequence | Unopened emails receive SMS at T+48h | Passed | Marketing Lead
FR-02.2 | OMNI-104 | Validate TCPA suppression during quiet hours | Dispatches between 9PM-8AM local time queued | Passed | Compliance Officer
FR-03.1 | OMNI-105 | Member SMS reply 'AGENT' routing to NICE CXone | Task routed to NICE CXone queue < 30s | Passed | Contact Center Ops